## Sheet1
Backlog ID | Task ID | Task Title: Description | Assigned To | Creation Week | Completion Week | Estimated Time (H) | Actual Time (H) | Status
D001 | 28 | R1 POST Endpoint: Endpoint (controller method) to create study session given session information. | JMatt26 | Week 1 | Week 1 | 0.25 | 0.5 | done
| 29 | R1 Service: Service method that creates and stores in DB a study session given session infromation. | JMatt26 | Week 1 | Week 1 | 0.75 | 1 | review
| 30 | R1 Unit Testing for #29 | JMatt26 | Week 1 |  | 0.75 |  | in progress | UserName | Student Full Name
| 31 | R1 Postman Testing for #28 | JMatt26 | Week 1 |  | 0.25 |  | in progress | mahirul101 | Mahirul Islam
D002 | 3 | R2 POST Endpoint: Endpoint gets username from jwt and adds it to session from session ID | JMatt26 | Week 1 | - | 0.25 |  | in progress | JMatt26 | Jared Matthews
| 22 | R2 Service: Service method to add a user to a session given the sessionID and username. | JMatt26 | Week 1 | - | 0.75 |  | in progress | letaoli123 | Le Tao Li
| 23 | R2 Unit Testing for #22 | JMatt26 | Week 1 | - | 0.75 |  | in progress | jastaggart | Jasmine Taggart
| 24 | R2 Postman Testing for #3 | JMatt26 | Week 1 | - | 0.25 |  | in progress | savperera369 | Saviru Perera
D003 | 4 | R3 GET Endpoint: Return all users registered for a session given session ID | KristianMyzeqari | Week 1 | - | 0.25 |  | in progress | Plangari | Parsa Langari
| 25 | R3 Service: Retrieve from DB all the users registered at a session given session ID. | KristianMyzeqari | Week 1 | - | 0.75 |  | in progress | nicholasmurphy2 | Nicholas Murphy
| 26 | R3 Unit Testing for #25 | KristianMyzeqari | Week 1 | - | 0.75 |  | in progress | KristianMyzeqari | Kristian Myzeqari
| 27 | R3 Postman Testing for #4 | KristianMyzeqari | Week 1 | - | 0.25 |  | in progress | smahm01 | Sadek Mahmood
D004 | 5 | R4 POST Endpoint: Create Account for user given user info (name + unique username + password). | PLangari, nicholasmurphy2 | Week 1 | Week 1 | 0.25 | 0.1 | done | massderrico | Massimo D'Errico
| 32 | R4 Service: Service methods to enable user creation given information | PLangari, nicholasmurphy2 | Week 1 | Week 1 | 0.75 | 0.5 | done
| 33 | R4 Unit Testing for #32 | PLangari, nicholasmurphy2 | Week 1 | Week 1 | 0.75 | 0.75 | done
| 34 | R4 Postman Testing for #5 | PLangari, nicholasmurphy2 | Week 1 |  | 0.25 |  | in progress
D005 | 6 | R5 GET Endpoint: Return TOs of all sessions that have not happened yet (upcoming sessions). | smahm01 | Week 1 |  | 0.25 |  | in progress
| 35 | R5 Service: Retrieve from DB all sessions whose dates + times have not been reached given current time. | smahm01 | Week 1 |  | 0.75 |  | in progress
| 37 | R5 Unit Testing for #35 | smahm01 | Week 1 |  | 0.75 |  | in progress
| 39 | R5 Postman Testing for #7 | smahm01 | Week 1 |  | 0.25 |  | in progress
| 7 | R5 GET Endpoint: Sends TO of all sessions that are happening right now (active sessions). | smahm01 | Week 1 |  | 0.25 |  | in progress
| 36 | R5 Service: Retrieve from DB all sessions whose dates + times are in the current time. | smahm01 | Week 1 |  | 0.75 |  | in progress
| 38 | R5 Unit Testing for #36 | smahm01 | Week 1 |  | 0.75 |  | in progress
| 40 | R5 Postman Testing for #6 | smahm01 | Week 1 |  | 0.25 |  | in progress
D006 | 8 | R6 GET Endpoint: Return all the study sessions owned by or participated by current user's friends. | JMatt26 | Week 1 |  | 0.25 |  | in progress
| 41 | R6 Service: Service methods that return all the sessions linked to current user's friends. | JMatt26 | Week 1 |  | 0.75 |  | in progress
| 42 | R6 Unit Testing for #41 | JMatt26 | Week 1 |  | 0.75 |  | in progress
| 43 | R6 Postman Testing for #8 | JMatt26 | Week 1 |  | 0.25 |  | in progress
D007 | 9 | R7 Non-Functional Test: Does adding user to study session take less than 1.5 seconds? | - | Week 1 |  | 0.25 |  | in progress
D008 | 10 | R8 DELETE Endpoint: If user making request is admin, delete session by ID. | letaoli123 | Week 1 |  | 0.5 |  | in progress
| 44 | R8 Service: Service methods that delete a session given the admin's ID. | letaoli123 | Week 1 |  | 1 |  | in progress
| 45 | R8 Unit Testing for #44 | letaoli123 | Week 1 |  | 0.75 |  | in progress
| 46 | R8 Postman Testing for #10 | letaoli123 | Week 1 |  | 0.25 |  | in progress
D009 | 11 | R9 PUT Endpoint: Remove user from session by session ID, given username. | mahirul101 | Week 1 |  | 0.25 |  | in progress
| 47 | R9 Service: Service method that removes user from session's registered participant list given username. | mahirul101 | Week 1 |  | 0.75 |  | in progress
| 48 | R9 Unit Testing for #47 | mahirul101 | Week 1 |  | 0.75 |  | in progress
| 49 | R9 Postman Testing for #11 | mahirul101 | Week 1 |  | 0.25 |  | in progress
D010 | 12 | R10 GET Endpoint: Returns TOs of all study sessions that have a course name as a property in session information. | savperera369 | Week 1 |  | 0.5 |  | in progress
| 50 | R10 Service: Retrieve all sessions whose session information contain a course name (input). | savperera369 | Week 1 |  | 1 |  | in progress
| 51 | R10 Unit testing for #50 | savperera369 | Week 1 |  | 0.75 |  | in progress
| 52 | R10 Postman Testing for #12 | savperera369 | Week 1 |  | 0.25 |  | in progress
D011 | 13 | R11 PUT/POST Endpoint: Mark session as full when max capacity of session is reached. | jastaggart | Week 1 |  | 0.25 |  | in progress
| 53 | R11 Service: Service method that counts the number of a session's participants, marks as full if capacity reached. | jastaggart | Week 1 |  | 0.75 |  | in progress
| 54 | R11 Unit Testing for #53 | jastaggart | Week 1 |  | 0.75 |  | in progress
| 55 | R11 Postman Testing #13 | jastaggart | Week 1 |  | 0.25 |  | in progress
D012 | 14 | R12 Postman: Making sure sign in flow works well | PLangari | Week 1 |  | 0.25 | 0.25 | done
NA | 17 | Start the figma design for front end design | jastaggart, JMatt26, massderrico | Week 1 |  | 3 |  | in progress
NA | 20 | Initialize front end project: Create react native expo project and add to application | PLangari | Week 1 | Week 1 | 0.25 | 0.25 | done
NA | 16 | Program Enum: Add Enum Type for Department of a user's study field. | letaoli123 | Week 1 | Week 1 | 0.25 | 0.25 | done
NA | 15 | Department Enum : Add Enum Type for Department of a user's study field. | nicholasmurphy2 | Week 1 | Week 1 | 0.25 | 0.25 | done